FRANKSTON 2035 — ART THAT LIVES

Council Pitch Document

For: Frankston City Council officers and Councillors

Prepared by: Blue Snake Studio

Date: June 2026

IN ONE SENTENCE

Frankston 2035 is a ten-year creative infrastructure program that puts permanent art in schools, healthy technology in libraries, and self-guided creative walks in the city's streets — starting with three fully scoped pilots.

THE PROBLEM

Frankston has creative people. It lacks the infrastructure to connect them.

— Young people in Frankston have fewer publicly funded creative opportunities than comparable Victorian cities.

— Technology in schools and libraries increasingly extracts children's data and attention, without returning lasting creative value.

— Public art exists in Frankston — but it does not teach, it does not connect, and it does not grow.

This is not a criticism. It is a structural gap that other cities have closed. Frankston can close it too.

THE OPPORTUNITY

Three forces are converging:

CULTURAL: Post-pandemic demand for place-based meaning. Public art investment is resurging nationally. Communities want to see themselves reflected in their city.

TECHNOLOGICAL: Growing concern about children's digital safety. Parents, teachers, and councils are actively looking for alternatives to platform-based technology in learning environments.

FUNDING: Creative Victoria, Australia Council, and federal place-based investment programs are actively seeking proposals in exactly this space. The window is open.

THE THREE PILOTS

PILOT 01 — THE LIVING MURAL

A curriculum-linked mural co-designed with students in a Frankston primary school.

Where: A Frankston primary school (site to be confirmed with Council)

Timeline: 12 months from commission

What's permanent: Large-scale mural + curriculum resource pack owned by the school

Budget: $45,000–$65,000

Council role: Facilitate school relationship + permit support

Who owns it: The school, permanently

The mural is not decoration. It is built around curriculum content. Students co-design it. Teachers use it. The artist is credited. The wall teaches long after BSS has left.

PILOT 02 — THE HEALTHY TECH LIBRARY

A dedicated creative technology space in Frankston Library — no accounts, no tracking, no advertising.

Where: Frankston Library

Timeline: 6 months setup + ongoing programming

What's permanent: Installed space + trained facilitators + ongoing program owned by the Library

Budget: $30,000–$50,000

Council role: Facilitate library partnership

Who owns it: Frankston Library Service, permanently

Every tool meets the Healthy Technology Charter. Drawing. Music. Writing. Building. No child creates an account. The screen is a doorway, not a destination.

PILOT 03 — THE QR ART WALK

A self-guided creative walk through Frankston using QR codes to surface local stories, artworks, and audio.

Where: Frankston CBD and foreshore

Timeline: 6 months development + permanent installation

What's permanent: 10–15 QR stops + printed map + expandable web system

Budget: $20,000–$35,000

Council role: Site access + signage permits

Who owns it: The city and community, permanently

No app. No download. Content created by local artists and community members. New stops can be added by anyone following the system. Owned by Frankston, not by a platform.

BUDGET SUMMARY

Pilot 01 — Living Mural: Council co-investment $25,000–$35,000 + BSS/grants for balance

Pilot 02 — Healthy Tech Library: Council co-investment $15,000–$25,000 + BSS/grants for balance

Pilot 03 — QR Art Walk: Council co-investment $10,000–$15,000 + BSS/grants for balance

Total Council pilot contribution: $50,000–$75,000 (BSS contributes + grant-matched, target 2:1)

All estimates include 15% contingency.

WHAT WE ARE ASKING COUNCIL TO DO

Four asks. One is financial. Three cost nothing but a decision.

1. PARTNERSHIP STATEMENT

Name Frankston 2035 as a Council-supported initiative. Zero financial cost.

2. CO-INVESTMENT

Contribute $50,000–$75,000 across the three pilots. One line item, matched 2:1.

3. PERMIT FACILITATION

One nominated officer to assist with site access. 2–3 hours of staff time total.

4. HEALTHY TECHNOLOGY ALIGNMENT

A Council statement that child-facing programs are evaluated against the Healthy Technology Charter. Zero cost. Significant credibility.

We are not asking Council to run this project. We are asking Council to believe in it, open doors, and share in the outcome.

WHAT COUNCIL RECEIVES

Partnership endorsement → First-mover credibility in civic creativity nationally

Co-investment → Three permanent public assets, 2:1 matched

Permit facilitation → 2–3 hours of staff time

Healthy Technology statement → Alignment with national children's digital safety agenda

WHY START WITH THE LIBRARY CREATIVE PACK

Recommended first pilot: a curated set of offline creative tools installed in Frankston Library.

Cost: $20,000–$30,000 total. Council contribution: $12,000–$15,000.

Timeline: 3–4 months from decision to open.

Why first: Single partner. No software development. No First Nations cultural content requirements. Visible, permanent outcome. Demonstrates the project's philosophy immediately. Builds the Library relationship.

WHAT WE KNOW AND WHAT WE DON'T

QR walk delivery model works — PROVEN

BSS has the capability to deliver — PROVEN (component skills)

Murals can function as teaching tools — DRAFT (methodology sound, not yet tested in Frankston)

Public art increases community belonging — DRAFT (well-supported in literature, not yet measured locally)

Budget estimates are realistic — DRAFT (benchmarked against NAVA rates, not yet supplier-quoted)

All claims are tracked in the Proof Register. No claim is overstated.

WHAT PROTECTS THIS PROJECT

FIRST NATIONS PROTOCOL: A documented 9-part process governing all engagement with First Nations community. The process begins with listening, not content creation. No cultural material is used without explicit written permission.

HEALTHY TECHNOLOGY CHARTER: Three-question test applied to every technology used near children. Fail any question: the technology is rejected.

RISK REGISTER: Full risk tracking across strategic, operational, cultural, financial, and pitch-stage risks.

THE NEXT STEP

A 45-minute conversation. No commitment required.

— Council officer reviews this document

— 45-minute meeting scheduled (BSS will prepare agenda)

— Outcome: proceed / conditions / not right now

— If proceed: partnership statement drafted within 30 days

Contact: Blue Snake Studio — bluesssnakestudio@gmail.com

Frankston 2035 — Art That Lives

Council Pitch Document v1.0 — June 2026

Blue Snake Studio