FRANKSTON 2035 — ART THAT LIVES

Public Art Pilot Proposal

For: Artists, arts administrators, funders, and public art committees

Prepared by: Blue Snake Studio

THE PROPOSAL

Three public art pilots. Three permanent outcomes. One city transformed.

Frankston 2035 is not a public art program. It is a civic creativity system that uses public art as one of its primary instruments. The difference is that everything produced is permanent, curriculum-linked, community-owned, and designed to grow.

PILOT 01 — THE LIVING MURAL

THE BRIEF

Commission a professional artist to create a large-scale mural at a Frankston primary school.

The mural is co-designed with students. It is curriculum-linked — the visual content is built around learning areas identified by the school's teachers. It is permanent. After installation, it belongs to the school.

ARTISTIC METHODOLOGY

Co-design, not consultation.

Students are not surveyed and ignored. Their contributions drive the content. At minimum, one student-originated element must appear in the final artwork unchanged. This is a non-negotiable condition of commission.

Curriculum as content.

The artist works with teachers before beginning the design. The mural carries information — mathematical patterns, historical references, local ecology, language — embedded in visual form. This is what makes the wall teach.

Artist as educator.

The commissioned artist spends at least two sessions in the school before beginning — not to teach art, but to listen. To learn what the school cares about. The design comes after.

ARTIST BRIEF (SUMMARY)

Artists commissioned are:

— Australian-based (Frankston or greater Victoria preferred)

— Experienced in large-format exterior or interior installation

— Comfortable with participatory and co-design processes

— Prepared to credit the school's students as co-designers in all public documentation

Artist fees benchmarked against NAVA recommended rates.

BUDGET

Artist fee (concept to completion): $25,000–$35,000

Materials and consumables: $5,000–$8,000

Community facilitation and co-design: $5,000–$10,000

Documentation and curriculum pack: $5,000–$7,000

Permits, insurance, scaffolding: $5,000

Total: $45,000–$65,000

DELIVERABLES

— One installed mural (permanent, on school property)

— One curriculum resource pack (teacher edition + student activity sheets)

— One artist documentation set (statement, process diary, photographs)

— One replication guide

PILOT 03 — THE QR ART WALK

THE BRIEF

Commission local artists and community members to create content for a self-guided creative walk through Frankston's CBD and foreshore.

10–15 QR-coded stops. Each stop opens a static web page — no app, no account, no tracking — featuring original artwork, audio, photography, or writing by local contributors.

ARTISTIC METHODOLOGY

Community-nominated sites.

Stops are not chosen by BSS or Council. They are nominated by the community: What places in Frankston matter to you? What story should be told here?

Multiple content forms.

Each stop can carry: original artwork (digital or photographed), audio recordings (music, spoken word, oral history), photography (with consent), writing (short form — poetry, place essays, personal histories).

No platform dependency.

All content hosted on static web pages. Files are small. Pages load on slow connections. If hosting ever fails, content can be moved in an afternoon. Nothing locked in a proprietary platform.

Community additions.

After launch, new stops can be added by community members following the documented process. System designed to grow without BSS.

BUDGET

Content creation (commissioning local artists): $10,000–$15,000

Web build (static pages, QR system): $3,000–$5,000

Print (map, QR plaques): $2,000–$3,000

Physical installation (signage, weather-proofing): $2,000–$4,000

Documentation and replication guide: $3,000–$5,000

Total: $20,000–$35,000

DELIVERABLES

— 10–15 installed QR stops with weather-proof signage

— Static web system with all content hosted and documented

— Printed community map (A3, saddle-stitched, free distribution)

— Community contribution guide

— Replication guide

PILOT 02 — THE HEALTHY TECH LIBRARY

THE BRIEF

Install a dedicated creative technology space in Frankston Library. All tools are free, offline-capable, account-free, and ad-free. The library becomes a studio.

WHAT IS INSTALLED

A curated suite of creative software on dedicated library workstations, plus:

— One printed guide per tool (laminated, at the station)

— One parent guide (take-home)

— One facilitator manual (for trained library staff)

No specialist hardware beyond standard library computers. No ongoing software licensing costs (all tools are open-source or free).

BUDGET

Tool evaluation and curation: $3,000–$5,000

Space design and signage: $5,000–$8,000

Facilitator training: $5,000–$8,000

Print materials: $2,000–$3,000

Documentation: $5,000–$8,000

Contingency: $5,000–$8,000

Total: $25,000–$40,000

Note: Library Creative Pack (recommended first pilot) is a minimum viable version at $20,000–$30,000.

DELIVERABLES

— Installed and operational creative technology space

— Trained library facilitators (minimum 3)

— Parent and community guide

— Facilitator manual

— Six-month program report

— Replication guide

WHAT ALL THREE PILOTS SHARE

1. PERMANENT OUTCOME. Nothing in Frankston 2035 produces only an event or a report.

2. COMMUNITY OWNERSHIP. Every asset transfers to the community institution on completion.

3. REPLICATION GUIDE. Every pilot allows another school, library, or city to duplicate it without BSS involvement.

RECOMMENDED SEQUENCE

Start here: Library Creative Pack (reduced Pilot 02). $20,000–$30,000. 3–4 months. Single partner. Proves the model.

Then: QR Art Walk (Pilot 03). $20,000–$35,000. 6 months.

Then: Living Mural (Pilot 01). $45,000–$65,000. 12 months. Requires confirmed school relationship.

FUNDING STRATEGY

Frankston City Council — Co-investment — Proposal stage

Creative Victoria (Place-Based grants) — Grant — Not yet applied

Australia Council for the Arts (Communities fund) — Grant — Not yet applied

Philanthropic (local business sponsorship) — Not yet approached

Blue Snake Studio contribution — In-kind + cash — Committed

No pilot begins without confirmed Council partnership.

CONTACT

Blue Snake Studio

bluesssnakestudio@gmail.com

Frankston 2035 — Art That Lives

Public Art Pilot Proposal v1.0 — June 2026

Blue Snake Studio