FRANKSTON 2035 — ART THAT LIVES

Print Pack Index

A complete index of all print assets — what needs to be designed, what specs exist, what's still pending.

DESIGN SYSTEM REFERENCE

All print assets must conform to the Publication Design Guide.

Display type: Canela Light / Canela Regular

Body type: Neue Haas Grotesk

Data/labels: IBM Plex Mono

Palette:

Deep Ink #1A1A1A

Warm White #F8F6F1

Frankston Blue #1B4F8A

Coastal Sand #D4C4A0

Approval Green #3A7D44

Caution Amber #C97D1A

Stop Red #B83232

Data Grey #6B6B6B

Grid: 12-column, A4, 15mm outer margins, 10mm inner margins

Photography: Documentary, natural light. No stock photography.

PRIORITY 1 — COUNCIL PITCH MATERIALS

1. Hero System Diagram

Format: A4 landscape / 16:9 / A6 postcard

Status: Specified — not yet designed

Notes: SVG. Export as PDF + PNG 300dpi. The keystone visual. Design this first.

2. Pilot Menu One-Pager

Format: A3 or 2×A4

Status: Text complete — not yet laid out

Notes: Print for Council meeting.

3. Council Deck Slides

Format: 16:9 digital presentation

Status: Scaffold complete — not yet designed

Notes: Keynote or PowerPoint using publication design guide.

4. Council Pitch Leave-Behind

Format: A4 booklet, saddle-stitched

Status: Text complete — not yet laid out

Notes: Back cover should feature the Hero Diagram.

PRIORITY 2 — COMMUNITY AND PUBLIC MATERIALS

5. QR Art Walk Community Map

Format: A3 folded to DL carry size

Status: Not yet designed

Notes: Full bleed Frankston foreshore/CBD map. QR stop markers. Print run 500–1,000.

6. QR Stop Signage (weather-proof)

Format: 200×200mm powder-coated aluminium

Status: Not yet designed

Notes: Project logo, QR code, stop number, short title. UV resistant.

7. Library Creative Pack Signage

Format: A3 poster + A5 desk cards

Status: Not yet designed

Notes: "How this space works" + individual tool guides.

8. Community Participation Flyer

Format: A5 double-sided

Status: Not yet designed

Notes: For schools and library distribution. "How to get involved."

PRIORITY 3 — PROGRAM AND EDUCATIONAL MATERIALS

9. Curriculum Resource Pack

Format: A4 saddle-stitched, 8–12pp

Status: Not yet designed

Notes: Developed with school post-commission. Mural-linked lesson plans + student activity sheets.

10. Parent Guide (Healthy Tech Library)

Format: A5 double-sided

Status: Not yet designed

Notes: "What your child does here and why it's safe."

11. Facilitator Manual (Library)

Format: A4 spiral-bound

Status: Not yet designed

Notes: Staff-facing. Laminated tab dividers.

12. Artist Documentation Pack

Format: A4, digital-first with print option

Status: Not yet designed

Notes: Process diary template, artist statement template, photo spec.

PRIORITY 4 — IDENTITY AND SIGNAGE

13. Project Identity Mark

Format: Vector (SVG/EPS)

Status: Not yet designed

Notes: Wordmark only — "Frankston 2035" in Canela, "Art That Lives" in Neue Haas. No icon.

14. Mural Dedication Plaque

Format: 200×100mm engraved metal

Status: Not yet designed

Notes: School name, mural title, artist credit, BSS credit, year.

15. QR Walk Launch Poster

Format: A2, outdoor-safe

Status: Not yet designed

Notes: For library, council buildings, school noticeboards.

RECOMMENDED DESIGN SEQUENCE

1. Hero System Diagram (SVG) — keystone visual, everything references it

2. Project identity mark — needed before any public materials print

3. Council Deck slides — needed before the Council pitch meeting

4. Pilot Menu one-pager — one sheet, fast to produce

5. QR Art Walk map — needed for Pilot 03, not urgent until confirmed

STATUS TRACKING

Use these status markers:

Specified → In Design → Approved → Print-Ready → Printed

Update this document as each asset progresses.

PRINT PRODUCTION NOTES

Preferred: print on demand for initial runs. Offset only when run exceeds 500 units.

Paper: 120gsm uncoated for text documents. 350gsm for posters and covers.

Colour: CMYK conversions from hex values in Publication Design Guide.

Accessibility: All text must meet WCAG 2.1 AA contrast ratios. No text below 9pt in print.

Frankston 2035 — Art That Lives

Print Pack Index v1.0 — June 2026

Blue Snake Studio

Update as assets are produced.